## Sheet1
Priority 1 Tasks
Task Description | Orig Est | Curr Est | Elapsed | Remain | Completed
Fixing ProcessSmpGetPacket to remove the consumed message, Add messages being able to be consumed | 20 | 30 | 30 | 0 | Yes
Server only displays all messages no matter priority that is selected to display, Add priority filtering | 20 | 15 | 15 | 0 | Yes
Server crashes when 'Messages.txt' doesn’t exist and the show messages button is pressed | 5 |  | 3 | 0 | Yes
Server does not notify user when there are no messages to display | 10 | 10 | 10 | 0 | Yes
Consumer crashes when server is offline, does not notify user | 10 | 20 | 22 | 0 | Yes
Conumer crashes when requesting a message priority that isnt in the file | 20 | 15 | 14 | 0 | Yes
Producer crashes when server is offline, need message box to display no message available | 5 | 5 | 4 | 0 | Yes